## Team Overview
LAB 5 - TEAM WORK ALLOCATION PLAN
SQL Server Developer ¦ T-SQL Control Flow & Data Structures ¦ AdventureWorks2022 ¦ ProductionOps Schema
Course | SQL Server Developer |  | Database | AdventureWorks2022
Schema | ProductionOps |  | Timeline | 7 Days
Team Size | 9 Members |  | Workload Each | 11 SP
Total Story Points | 99 |  | Total Hours | 56
TEAM MEMBER ASSIGNMENTS (each task owned by ONE person only)
# | Member | Role | Lab Task(s) | Scripts / Deliverables | SP | Hrs
1 | Hassana | Schema & Failed Queue Developer | Task 1, Task 10 | initialize_productionops_schema.sql failed_inspection_queue.sql | 11 | 14
2 | Sahashri | Inspection & Temp Batch Developer | Task 2, Task 6 | inspection_request_registration.sql inspection_batch_processing.sql | 11 | 7
3 | Brain | Control Flow Developer | Task 3, Task 4 | inspection_result_classification.sql monthly_inspection_schedule.sql | 11 | 4
4 | Parth | Error Handling Developer | Task 5 | error_log.sql inspection_error_logging.sql | 11 | 7
5 | Josovo | Reporting & Views Developer | Task 8, Task 9 | product_quality_statistics.sql vProductInspectionSummary.sql | 11 | 4
6 | Lien | Release Review Table Developer | Task 12 | product_release_review.sql | 11 | 4
7 | Kelvin | Categories & Notification Developer | Task 7, Task 13 | inspection_category_management.sql notification_log.sql inspection_notification_cursor.sql | 11 | 4
8 | Dhruv | Failed Review Cursor Developer | Task 11 | failed_product_review_cursor.sql | 11 | 7
9 | Sahil | Deployment & Final Submission (LAST) | Task 14 + Final Submission | deploy_all.sql validate_lab5_results.sql README.md Data Mapping Screenshots (15) QA Review | 11 | 7
TEAM TOTAL (9 members x 11 SP each) | [5 empty] | 56

## Script Assignment
SCRIPT ASSIGNMENT MATRIX
One row per script file - unique task ownership
Lab Task | Script File | Folder Path | Owner | Type | SP | Status
Task 1 | initialize_productionops_schema.sql | scripts/setup/ | Hassana | Schema | 11 | Not Started
Task 10 | failed_inspection_queue.sql | scripts/tables/ | Hassana | Table | 11 | Not Started
Task 2 | inspection_request_registration.sql | scripts/tables/ | Shrili | Table | 11 | Not Started
Task 6 | inspection_batch_processing.sql | scripts/temporary_objects/ | Shrili | Temp Table | 11 | Not Started
Task 3 | inspection_result_classification.sql | scripts/controlflow/ | Brain | Control Flow | 11 | Not Started
Task 4 | monthly_inspection_schedule.sql | scripts/controlflow/ | Brain | Control Flow | 11 | Not Started
Task 5 | error_log.sql | scripts/tables/ | Parth | Table | 11 | Not Started
Task 5 | inspection_error_logging.sql | scripts/errorhandling/ | Parth | Error Handling | 11 | Not Started
Task 8 | product_quality_statistics.sql | scripts/reporting/ | Josovo | Derived Table | 11 | Not Started
Task 9 | vProductInspectionSummary.sql | scripts/reporting/ | Josovo | View | 11 | Not Started
Task 12 | product_release_review.sql | scripts/tables/ | Lien | Table | 11 | Not Started
Task 7 | inspection_category_management.sql | scripts/temporary_objects/ | Kelvin | Table Variable | 11 | Not Started
Task 13 | notification_log.sql | scripts/tables/ | Kelvin | Table | 11 | Not Started
Task 13 | inspection_notification_cursor.sql | scripts/cursors/ | Kelvin | Cursor | 11 | Not Started
Task 11 | failed_product_review_cursor.sql | scripts/cursors/ | Dhruv | Cursor | 11 | Not Started
Task 14 | deploy_all.sql | scripts/deployment/ | Sahil (LAST) | Deployment | 11 | Not Started
Task 14 | validate_lab5_results.sql | scripts/validation/ | Sahil (LAST) | Validation | 11 | Not Started
Final | README.md + Data Mapping + Screenshots + QA | Lab5/ | Sahil (LAST) | Final Submission | 11 | Not Started
NOTE: Each member = 11 SP total across their scripts

## Dependencies
WORK DEPENDENCY MAP
What must finish before the next task can start
Task | Owner | Depends On | Blocks
Task 1 - Schema | Hassana | None | All members
Task 10 - Failed Queue | Hassana | Task 1 | Task 11 (Dhruv)
Task 2 - Inspection Requests | Shrili | Task 1 | Validation
Task 6 - Temp Batch | Shrili | Task 1 | Task 14 (Sahil)
Task 3 - IF/ELSE | Brain | Task 1 | Task 14 (Sahil)
Task 4 - WHILE | Brain | Task 1 | Task 14 (Sahil)
Task 5 - Error Logging | Parth | Task 1 | Task 14 (Sahil)
Task 8 - Derived Tables | Josovo | Task 1 | Task 14 (Sahil)
Task 9 - View | Josovo | Task 1 | Task 14 (Sahil)
Task 12 - Release Review | Lien | Task 1 | Task 11 (Dhruv)
Task 7 - Table Variables | Kelvin | Task 1 | Task 14 (Sahil)
Task 11 - Review Cursor | Dhruv | Task 10 + 12 | Task 13 (Kelvin)
Task 13 - Notification | Kelvin | Task 11 | Task 14 (Sahil)
Task 14 - Final Submission | Sahil (LAST) | Tasks 1-13 | GitHub submission

## 7-Day Timeline
7-DAY SPRINT TIMELINE
Start: June 10, 2026 ¦ Equal workload: 11 SP
Day | Date | Phase | Member | Work Item | Exit Criteria
Day 1 | 2026-06-10 | Foundation | Hassana | Task 1 - Schema | Schema tested
Day 1 | 2026-06-10 | Foundation | Shrili | Task 2 - InspectionRequests | 10 inserts done
Day 1 | 2026-06-10 | Foundation | Lien | Task 12 - ProductReleaseReview | Table DDL done
Day 2 | 2026-06-11 | Development | Hassana | Task 10 - FailedInspectionQueue | Queue populated
Day 2 | 2026-06-11 | Development | Shrili | Task 6 - Temp Batch | Batch script done
Day 2 | 2026-06-11 | Development | Brain | Task 3 + 4 - IF/ELSE + WHILE | Control flow done
Day 2 | 2026-06-11 | Development | Parth | Task 5 - Error Logging | TRY/CATCH working
Day 2 | 2026-06-11 | Development | Josovo | Task 8 + 9 - Derived + View | Reporting done
Day 2 | 2026-06-11 | Development | Kelvin | Task 7 - Table Variables | Categories done
Day 3 | 2026-06-12 | Testing | All except Sahil | Test own scripts in SSMS | No errors
Day 4 | 2026-06-13 | Cursors | Dhruv | Task 11 - Review Cursor | All Pending processed
Day 4 | 2026-06-13 | Cursors | Kelvin | Task 13 - Notification Cursor | Notifications inserted
Day 5 | 2026-06-14 | Handoff | All | Push all scripts to GitHub | Repo complete
Day 6 | 2026-06-15 | Final Task | Sahil (LAST) | Task 14 - deploy + validate + README | Deployment green
Day 7 | 2026-06-16 | Submission | Sahil (LAST) | Screenshots + QA + submit link | Submitted to professor

## Story Points
STORY POINT BREAKDOWN
Equal split: every member = 11 story points / 7 hours
Member | Deliverable | SP | Sprint Day | Marks Covered
Hassana | Task 1 + Task 10 | 11 | Day 1-2 | Schema + Failed Queue
Shrili | Task 2 + Task 6 | 11 | Day 1-2 | Tables + Temp Batch
Brain | Task 3 + Task 4 | 11 | Day 2 | IF/ELSE + WHILE
Parth | Task 5 | 11 | Day 2 | Error Handling
Josovo | Task 8 + Task 9 | 11 | Day 2 | Derived + View
Lien | Task 12 | 11 | Day 1 | Release Review Table
Kelvin | Task 7 + Task 13 | 11 | Day 2-4 | Categories + Notification
Dhruv | Task 11 | 11 | Day 4 | Review Cursor
Sahil (LAST) | Task 14 + Final Submission | 11 | Day 6-7 | Deploy + Docs + QA
TOTAL |  |  | 56

## Screenshots
SCREENSHOT ASSIGNMENT
15 screenshots required ¦ Sahil compiles all for final submission
# | Description | Owner | Source Script | When | Filename | Status
1 | ProductionOps schema validation | Hassana | initialize_productionops_schema.sql | After Task 1 | 01_schema_validation.png | Not Started
2 | FailedInspectionQueue data | Hassana | failed_inspection_queue.sql | After Task 10 | 02_failed_queue.png | Not Started
3 | InspectionRequests data | Shrili | inspection_request_registration.sql | After Task 2 | 03_inspection_requests.png | Not Started
4 | #InspectionBatch temp table | Shrili | inspection_batch_processing.sql | After Task 6 | 04_inspection_batch.png | Not Started
5 | IF/ELSE classification results | Brain | inspection_result_classification.sql | After Task 3 | 05_if_else.png | Not Started
6 | WHILE monthly schedule | Brain | monthly_inspection_schedule.sql | After Task 4 | 06_while_schedule.png | Not Started
7 | ErrorLog contents | Parth | inspection_error_logging.sql | After Task 5 | 07_error_log.png | Not Started
8 | Derived table statistics | Josovo | product_quality_statistics.sql | After Task 8 | 08_quality_stats.png | Not Started
9 | vProductInspectionSummary view | Josovo | vProductInspectionSummary.sql | After Task 9 | 09_view_output.png | Not Started
10 | ProductReleaseReview table | Lien | product_release_review.sql | After Task 12 | 10_release_review.png | Not Started
11 | @InspectionCategories output | Kelvin | inspection_category_management.sql | After Task 7 | 11_categories.png | Not Started
12 | NotificationLog contents | Kelvin | inspection_notification_cursor.sql | After Task 13 | 12_notification_log.png | Not Started
13 | Review cursor execution | Dhruv | failed_product_review_cursor.sql | During Task 11 | 13_review_cursor.png | Not Started
14 | ProductReleaseReview after cursor | Dhruv | failed_product_review_cursor.sql | After Task 11 | 14_review_results.png | Not Started
15 | deploy_all.sql success | Sahil | deploy_all.sql | After Task 14 | 15_deploy_success.png | Not Started